## Resources
Estimates Calculator
As per https://rules.ssw.com.au/spec-do-you-know-how-to-give-the-customer-a-ballpark
Resource | Quantity | Standard | Pre-paid 40h | Development | Design | SysAdmin
Chief Architect |  | 285 | 270 | 1
Solution Architect | 1 | 265 | 250 | 1
Senior Software Architect | 1 | 225 | 210 | 1
Search Engine Optimization Expert |  | 225 | 210 | 1
User Experience Expert |  | 225 | 210 | 1
Senior System Administrator |  | 215 | 200 | 1
Software Architect |  | 195 | 180 | 1
System Administrator | 1 | 195 | 180 |  |  | 1
Senior Web/Graphic Designer | 1 | 195 | 180 |  | 1
Senior Software Developer |  | 175 | 160 | 1
Software Developer | 2 | 135 | 120 | 1
Areas
Design |  | 195 | 180
Development |  | 190 | 175
SysAdmin |  | 195 | 180
Note on A18: Danijel Malik: Rates are blended
Note on A19: Danijel Malik: Rates are blended

## Estimates
| Work Breakdown Structure | Estimate | MVP | Distribution | Standard | Pre-paid 40h | Standard (MVP) | Pre-paid 40h (MVP) | Is MVP | Area
| Total Cost | 743 | 347 |  | 142670 | 131525 | 66630 | 61425
- | Requirements | 450 | 210 | 60.52% | 87000 | 80250 | 40600 | 37450
| Task 1 | 10 | 10 |  | 1900 | 1750 | 1900 | 1750 | 1 | Development
| Task 2 | 20 | 20 |  | 3800 | 3500 | 3800 | 3500 | 1 | Development
| Task 3 | 40 | 40 |  | 7600 | 7000 | 7600 | 7000 | 1 | Development
| Task 4 | 80 | 0 |  | 15200 | 14000 | 0 | 0 | 0 | Development
[5 empty] | 0 | 0 | 0 | 0
| Task 1 | 10 | 10 |  | 1950 | 1800 | 1950 | 1800 | 1 | Design
| Task 2 | 20 | 20 |  | 3900 | 3600 | 3900 | 3600 | 1 | Design
| Task 3 | 40 | 40 |  | 7800 | 7200 | 7800 | 7200 | 1 | Design
| Task 4 | 80 | 0 |  | 15600 | 14400 | 0 | 0 | 0 | Design
[7 empty] | 0 | 0
| Task 1 | 10 | 10 |  | 1950 | 1800 | 1950 | 1800 | 1 | SysAdmin
| Task 2 | 20 | 20 |  | 3900 | 3600 | 3900 | 3600 | 1 | SysAdmin
| Task 3 | 40 | 40 |  | 7800 | 7200 | 7800 | 7200 | 1 | SysAdmin
| Task 4 | 80 | 0 |  | 15600 | 14400 | 0 | 0 | 0 | SysAdmin
- | General | 293 | 137 | 39.48% | 55670 | 51275 | 26030 | 23975
| Testing | 90 | 42 | 20% | 17100 | 15750 | 7980 | 7350 | 1 | Development
| Bug Fixes | 90 | 42 | 20% | 17100 | 15750 | 7980 | 7350 | 1 | Development
| DevOps | 45 | 21 | 10% | 8550 | 7875 | 3990 | 3675 | 1 | Development
| Project Management | 68 | 32 | 15% | 12920 | 11900 | 6080 | 5600 | 1 | Development
- | Total | 743 | 347 |  | 142670 | 131525 | 66630 | 61425
| MVP Total | 347 |  |  | 66630 | 61425
Note on E3: Danijel Malik: Best practice Requirements: 60% General: 40%
Note on E19: Danijel Malik: Best practice Requirements: 60% General: 40%